Fee-to-Trust

Quick Reference

Guide

Note: For Mandatory Acquisitions

refer to applicable policy and guidance to determine which steps are appropriate.

Release #13-90, Version III (rev 4), Issued 6/16/14

STEP 1

Encoding the Fee-to-Trust System of Record

Understanding the

STEP 2

Review of Written Request to Initiate Application Process

STEP 3

Responding to an Incomplete Case

STEP 4

Conducting Site Inspection and Completing Initial Certificate of Inspection (CIP)

May concurrently take Steps:

5. Preparing the Preliminary Title Opinion (PTO)

6. Preparing Notice of Application

7. Environmental Compliance Review

9. Clearance of PTO Objections before Notice of Decision (NOD)

STEP 5

Preparing the Preliminary Title Opinion (PTO)

STEP 6

Preparing Notice of Application

Must first complete steps:

1, 2, 3, and 4

BEFORE MOVING TO

STEPS 6 & 7

STEP 7

Environmental Compliance Review

Must first complete steps:

1, 2, 3, 4, and 6

BEFORE MOVING TO STEP 8

May concurrently take Steps:

5. Prepare PTO

7. ECRM

9. Clearance of PTO Objections before Notice of Decision (NOD)

9.  clearance of P

STEP 8

Comments to Notice of Application (NOA)

STEP 10

Preparing Analysis and Notice of Decision (NOD)

Must first complete steps:

1, 2, 3, 4 and 5

BEFORE MOVING TO STEP 9

Must first complete steps:

1-9

BEFORE MOVING TO STEP 10

May concurrently take Steps:

6. Prepare NOA

7. ECRM

8. Comments to Notice of Application

May concurrently take Steps:

12.  Prepare Final Certificate of Inspection and Possession.  However…No more than 180 days may pass between completion of Step 12 and completion of Step 13

May concurrently take Steps:

11.  Providing the Notice of Decision (& Notice of Publication).  However…No more than 180 days may pass between completion of Step 12 and completion of Step 13

STEP 9

Clearance of PTO Objections

before Notice of Decision (NOD)

STEP 11

Providing the Notice of the Decision (& Notice of Publication)

STEP 12

Preparing Final Certificate of Inspection and Possession (CIP)

Must first complete steps:

1-12

BEFORE MOVING TO STEP 13

No more than 180 days may pass between completion of Steps

12 & 13

STEP 13

Acceptance of Conveyance

STEP 14

Final Title Opinion and County Recordation

Must first complete steps:

9 and 13

BEFORE MOVING TO STEP 14

Must first complete step:

14

BEFORE MOVING TO STEP 15

Must first complete steps:

1-15

BEFORE MOVING TO STEP 16

STEP 13

Acceptance of Conveyance

STEP 14

Final Title Opinion and Recordation

STEP 15

Recording at Land Titles and Records Office

STEP 16

Completed Application Packet