## Project Status
[Bureau] [Program] Project Status
as of October 11, 2017
Project Name | Congressional District | Use one line per procurement vehicle | Appropriated Year(s) identify amounts per year in notes | Planned Amount | Total Award Amount | Obligated to Date (%) | Expended to Date (%) | Planned Award | Revised Award | Actual Award | Percent Complete | Planned Completion | Revised Completion | Actual Completion | Delivery (Y/N) if no, expected date | Contract Closeout (Y/N) | Notes
Example High School | ME-3 | Planning | 2011 | 250000 |  |  |  | 2012-01-17 | 2012-06-05 | 2012-06-05 | 100% | 2013-05-01 | 2015-03-01 | 2015-03-01
|  | Design | 2014 | 1344902 |  |  |  | 2015-03-02 | 2015-09-14 | 2015-09-14 | 70% | 2016-11-01 | 2018-01-18
|  | Construction | 2015 | 19380090 |  |  |  | 2017-04-01 | 2018-03-01
Example Day School | AZ-4 | Design/Build | 2016 | 14389000 |  |  |  | 2017-04-01 | 2018-03-01